## Schedule
Done in time | Completed late | To be done
In progress | Late | Started Early | Completed early
Activity / Deliverable | Responsible | Assistant | Status | Duration | Error margin | Total | Time taken | 2019-08-15 | 2019-08-22 | 2019-08-29 | 2019-09-05 | 2019-09-12 | 2019-09-19 | 2019-09-26 | 2019-10-03 | 2019-10-10 | 2019-10-17 | 2019-10-24 | 2019-10-31 | 2019-11-07 | 2019-11-14 | 2019-11-21 | 2019-11-28 | 2019-12-05 | 2019-12-12 | 2019-12-19
Project Inception | All |  | Done | bar: 2019-08-15 to 2019-08-29
Project specification | All |  | Done | bar: 2019-08-22 to 2019-09-12
Set up blog | Nicolas |  | Done | 2 | 0.6 | 2.6 | 2 | bar: 2019-09-05
Make Requirements Definition | Matheus |  | Done | 10 | 3 | 13 | 5 | bar: 2019-09-05 to 2019-09-12
Make Risk Analysis | Álefe |  | Done | 10 | 3 | 13 | 9 | bar: 2019-09-05 to 2019-09-12
Make Schedule | Nicolas |  | Done | 20 | 6 | 26 | 29 | bar: 2019-09-05 to 2019-09-12
Make Budget | Matheus |  | Done | 5 | 1.5 | 6.5 | 4 | bar: 2019-09-05 to 2019-09-12
Beautify blog | Nicolas |  | Done | 5 | 1.5 | 6.5 | 2
Write Project charter | All |  | Done | 10 | 3 | 13 | 5 | bar: 2019-09-05 to 2019-09-12
Write blog posts | All |  | Done | 4 | 1.2 | 5.2 | 12 | bar: 2019-09-05 to 2019-09-12
Prepare project charter presentation | Nicolas |  | Done | 2 | 0.6 | 2.6 | 1
Purchase and Gather Materials | All |  | Done | 10 | 3 | 13 | 8.3 | bar: 2019-09-05 to 2019-09-26
Project Charter | bar: 2019-09-05 to 2019-09-12
Total Time |  |  |  | 78 | 23.4 | 101.4 | 77.3 | bar: 2019-09-05 to 2019-09-12
Assemble robot base | Nicolas | Álefe | Done | 1 | 0.3 | 1.3 | 0.5 | bar: 2019-09-12 to 2019-09-26
Test power bank supply with RPi | Nicolas | Matheus | Done | 1 | 0.3 | 1.3 | 1 | bar: 2019-09-12 to 2019-09-26
Create robot mechanics model | Álefe | Nicolas | Done | 5 | 1.5 | 6.5 | 4 | bar: 2019-09-19 to 2019-09-26
Create power supply circuits | Matheus | Nicolas | Done | 3 | 0.9 | 3.9 | 4 | bar: 2019-09-19 to 2019-09-26
Test battery supply with motors | Matheus | Nicolas | Done | 1 | 0.3 | 1.3 | 1.5 | bar: 2019-09-19 to 2019-09-26
Create robot supporting structures | Álefe | Nicolas | Done | 3 | 0.9 | 3.9 | 6 | bar: 2019-09-19 to 2019-09-26
Model vehicle software | Nicolas | Álefe | Done | 4 | 1.2 | 5.2 | 8 | bar: 2019-09-19 to 2019-09-26
Set up vehicle programming environment | Nicolas | Álefe | Done | 2 | 0.6 | 2.6 | 2.5 | bar: 2019-09-19 to 2019-09-26
Model lock mechanics | Álefe | Matheus | Done | 2 | 0.6 | 2.6 | 1 | bar: 2019-09-19 to 2019-09-26
Create lock circuit | Matheus | Álefe | Done | 1 | 0.3 | 1.3 | 2 | bar: 2019-09-19 to 2019-09-26
Create lock control software | Nicolas | Álefe | Done | 1 | 0.3 | 1.3 | 2 | bar: 2019-09-19 to 2019-09-26
Assemble lock mechanics on container | Álefe | Nicolas | Done | 3 | 0.9 | 3.9 | 2 | bar: 2019-09-19 to 2019-09-26
Create item detection circuit | Matheus | Álefe | Done | 5 | 1.5 | 6.5 | 11 | bar: 2019-09-19 to 2019-10-03
Create item detection software | Nicolas | Matheus | Done | 2 | 0.6 | 2.6 | 0.5 | bar: 2019-09-19 to 2019-10-03
Attach item detection circuit to container | Álefe | Matheus | Done | 1 | 0.3 | 1.3 | 2.15 | bar: 2019-09-19 to 2019-10-03
Set up cloud server | Natan | Matheus | Done | 2 | 0.6 | 2.6 | 1.5 | bar: 2019-09-19 to 2019-09-26
Set up database on cloud server | Natan | Matheus | Done | 2 | 0.6 | 2.6 | 1.5 | bar: 2019-09-19 to 2019-09-26
Test item detection in vehicle | Nicolas | Álefe | Done | 1 | 0.3 | 1.3 | 0.5 | bar: 2019-09-26 to 2019-10-03
Create motor interface circuit | Matheus | Álefe | Done | 2 | 0.6 | 2.6 | 3
Test movement control through RPi | Nicolas | Álefe | Done | 4 | 1.2 | 5.2 | 3
Create ultrassound interface circuit | Matheus | Álefe | Done | 1 | 0.3 | 1.3 | 3
Make ultrassound software | Nicolas | Álefe | Done | 2 | 0.6 | 2.6 | 2.5 | bar: 2019-09-26 to 2019-10-03
Test ultrassound | Matheus | Nicolas | Done | 1 | 0.3 | 1.3 | 3 | bar: 2019-09-26 to 2019-10-03
Attach circuits to robot base | Álefe | Matheus | Done | 3 | 0.9 | 3.9 | 3
Create basic radio software | Nicolas | Álefe | Done | 3 | 0.9 | 3.9 | 3 | bar: 2019-09-26 to 2019-10-03
Test radio communication with RPi | Nicolas | Álefe | Done | 1 | 0.3 | 1.3 | 1.3 | bar: 2019-09-26 to 2019-10-03
Test power bank with all circuits | Matheus | Nicolas | Done | 5 | 1.5 | 6.5 | 1 | bar: 2019-09-26 to 2019-10-03
Test RPi camera | Nicolas | Matheus | Done | 1 | 0.3 | 1.3 | 1.5
Integrate hardware and mechanics | Álefe | Matheus | Done | 4 | 1.2 | 5.2 | 14.25 | bar: 2019-09-26 to 2019-10-10
Test vehicle movement w/ circuits and load | Nicolas | Álefe | Done | 4 | 1.2 | 5.2 | 7 | bar: 2019-09-26 to 2019-10-03
Model app software | Natan | Nicolas | Done | 6 | 1.8 | 7.8 | 4.8 | bar: 2019-09-26 to 2019-10-03
Create sketch of the app with Marvel | Natan | Nicolas | Done | 4 | 1.2 | 5.2 | 10.82
Model database tables | Natan | Álefe | Done | 3 | 0.9 | 3.9 | 4.55
Model server's software | Natan | Álefe | Done | 5 | 1.5 | 6.5 | 4.41 | bar: 2019-09-26 to 2019-10-10
Create model/drawing of the city | Álefe | Natan | Done | 3 | 0.9 | 3.9 | 4.5 | bar: 2019-09-26 to 2019-10-03
Write Partial Evaluation 1 report | All |  | Done | 10 | 3 | 13 | 7
Prepare Partial Evaluation 1 presentation | Nicolas |  | Done | 2 | 0.6 | 2.6 | 1
Partial Evaluation 1 | bar: 2019-09-19 to 2019-09-26
Total Time |  |  |  | 104 | 31.2 | 135.2 | 134.28
Set up computer vision environment | Nicolas | Álefe | Done | 4 | 1.2 | 5.2 | 10.5 | bar: 2019-09-26 to 2019-10-10
Test performance of CV on RPi | Nicolas | Álefe | Done | 5 | 1.5 | 6.5 | 2 | bar: 2019-09-26 to 2019-10-10
Test vehicle movement on the eva mats | Álefe | Matheus | Done | 2 | 0.6 | 2.6 | 0.75 | bar: 2019-09-26 to 2019-10-10
Make vehicle go in a straight line | Matheus | Natan | Done | 15 | 4.5 | 19.5 | 25.15 | bar: 2019-09-26 to 2019-10-10
Test visibility of colored tape on mat | Nicolas | Álefe | Done | 2 | 0.6 | 2.6 | 3 | bar: 2019-09-26 to 2019-10-03
Create city roads with tape | Natan | Matheus | Done | 4 | 1.2 | 5.2 | 4.67 | bar: 2019-09-26 to 2019-10-10
Create street recognition software | Nicolas | Álefe | Done | 10 | 3 | 13 | 52.8 | bar: 2019-09-26 to 2019-11-14
Test city visibility against background | Nicolas | Álefe | Done | 2 | 0.6 | 2.6 | 1 | bar: 2019-09-26 to 2019-10-10
Create robot-server communication protocol | Álefe | Natan | Done | 3 | 0.9 | 3.9 | 5.7 | bar: 2019-09-26 to 2019-10-17
Implement the app skeleton | Matheus | Nicolas | Done | 10 | 3 | 13 | 8 | bar: 2019-09-26 to 2019-10-17
Create basic account system | Natan | Matheus | Done | 4 | 1.2 | 5.2 | 18.5 | bar: 2019-09-26 to 2019-10-17
Create basic requests system | Natan | Matheus | Done - Blog | 10 | 3 | 13 | 36.84 | bar: 2019-10-10 to 2019-11-14
Make the vehicle follow the road | Álefe | Nicolas | Done - Blog | 5 | 1.5 | 6.5 | 26.9 | bar: 2019-10-10 to 2019-11-14
Create crossing recognition software | Álefe | Nicolas | Done - Blog | 10 | 3 | 13 | 45.4 | bar: 2019-10-10 to 2019-11-14
Make the vehicle do a turn | Matheus | Álefe | Done - Blog | 5 | 1.5 | 6.5 | 3.57 | bar: 2019-10-10 to 2019-10-24
Create street signs (qr codes) | Nicolas | Natan | Done | 3 | 0.9 | 3.9 | 3.5 | bar: 2019-10-10 to 2019-10-17
Test visibility of QR codes | Álefe | Nicolas | Done | 3 | 0.9 | 3.9 | 3.8 | bar: 2019-10-10 to 2019-10-17
Create street sign recognition software | Nicolas | Álefe | Done - Blog | 4 | 1.2 | 5.2 | 3.6 | bar: 2019-10-10 to 2019-11-14
Test robot-server communication | Álefe | Natan | Done - Blog | 3 | 0.9 | 3.9 | 15.1 | bar: 2019-10-10 to 2019-11-14
Create routing software | Natan | Matheus | Done - Blog | 15 | 4.5 | 19.5 | 2 | bar: 2019-10-17 to 2019-11-14
Make vehicle receive route from server | Álefe | Natan | Done - Blog | 8 | 2.4 | 10.4 | 1 | bar: 2019-10-10 to 2019-11-14
Create software to follow route | Natan | Matheus |  | 10 | 3 | 13 | bar: 2019-10-17 to 2019-11-14
Open box on server command | Matheus | Nicolas | Done - Blog | 5 | 1.5 | 6.5 | 4.3 | bar: 2019-10-17 to 2019-11-14
Create delivery item detection software | Matheus | Natan | Done - Blog | 2 | 0.6 | 2.6 | bar: 2019-10-17 to 2019-10-24
Update server on the robot status | Matheus | Natan | Done - Blog | 5 | 1.5 | 6.5 | 7 | bar: 2019-10-17 to 2019-11-14
Write Partial evaluation 2 report | All |  | Done | 10 | 3 | 13 | 18.1
Prepare Partial Evaluation 2 presentation | Nicolas |  | Done | 2 | 0.6 | 2.6 | 0.5
Partial Evaluation 2 | bar: 2019-09-26 to 2019-10-17
Total time |  |  |  | 161 | 48.3 | 209.3 | 303.68
Create the obstacles | Natan | Matheus |  | 3 | 0.9 | 3.9 | bar: 2019-10-24 to 2019-11-14
Create obstacle recognition software | Álefe | Nicolas |  | 15 | 4.5 | 19.5 | bar: 2019-10-24 to 2019-11-14
Make the vehicle avoid an obstacle | Álefe | Nicolas |  | 10 | 3 | 13 | bar: 2019-10-24 to 2019-11-14
Make vehicle decide if it can't follow route | Natan | Álefe |  | 5 | 1.5 | 6.5 | bar: 2019-10-24 to 2019-11-14
Create the traffic lights | Matheus | Natan | In progress | 3 | 0.9 | 3.9 | 15 | bar: 2019-10-17 to 2019-11-14
Create vehicle-choosing software | Matheus | Natan | Done | 10 | 3 | 13 | 1 | bar: 2019-10-24 to 2019-11-14
Create traffic light recognition software | Álefe | Nicolas | In progress | 10 | 3 | 13 | 2 | bar: 2019-10-24 to 2019-11-14
Integrate the vision components | Nicolas | Álefe | In progress | 10 | 3 | 13 | 17.95 | bar: 2019-10-31 to 2019-11-14
Integrate robot software modules | All |  | In progress | 10 | 3 | 13 | 14.6 | bar: 2019-10-17 to 2019-11-14
Implement app account creation | Natan | Matheus | Done - Blog | 10 | 3 | 13 | 7.2 | bar: 2019-10-31 to 2019-11-14
Create app delivery creation software | Natan | Matheus |  | 5 | 1.5 | 6.5 | bar: 2019-10-31 to 2019-11-14
Create app delivery finish software | Natan | Matheus |  | 5 | 1.5 | 6.5 | bar: 2019-10-31 to 2019-11-14
Create app delivery tracking software | Matheus | Natan |  | 6 | 1.8 | 7.8 | bar: 2019-10-31 to 2019-11-14
Update the app on the delivery status | Matheus | Natan |  | 10 | 3 | 13 | bar: 2019-11-07 to 2019-11-14
Integration of all parts | All |  |  | 20 | 6 | 26 | 5.3 | bar: 2019-11-07 to 2019-11-14
Write Partial Evaluation 3 report | All |  |  | 6 | 1.8 | 7.8 | 0.5 | bar: 2019-11-07 to 2019-11-14
Write Technical Report | All |  |  | 30 | 9 | 39 | 24.2 | bar: 2019-09-19 to 2019-11-14
Prepare Partial Evaluation 3 presentation | Nicolas |  |  | 2 | 0.6 | 2.6 | 3 | bar: 2019-11-07 to 2019-11-14
Shoot Video | All |  |  | 10 | 3 | 13 | bar: 2019-11-07 to 2019-11-14
Partial Evaluation 3 | bar: 2019-10-24 to 2019-11-14
Total Time |  |  |  | 180 | 54 | 234 | 90.75
Prepare Final Evaluation presentation | Nicolas |  |  | 20 | 6 | 26 | bar: 2019-11-14 to 2019-11-28
Final Evaluation | bar: 2019-11-14 to 2019-11-28
Total Time |  |  |  | 20 | 6 | 26
TOTAL TOTAL |  |  |  | 465 | 139.5 | 604.5 | 606.01

## Worked hours
First Evaluation
Members | Estimated Hours | Worked hours
Nicolas | 40.9 | 37
Álefe | 34.4 | 30.25
Nathan | 31.9 | 19
Matheus | 28 | 16
Total | 135.2 | 102.25
Second Evaluation
Members | Estimated Hours | Worked hours
Nathan | 58.9 | 37.58
Matheus | 57.6 | 41.15
Álefe | 47.2 | 64.65
Nicolas | 45.6 | 84.85
Total | 209.3 | 228.23
Third Evaluation
Members | Estimated Hours | Worked hours
Álefe | 48.5 | 70.35
Matheus | 40.7 | 34.91
Nathan | 39.4 | 69.34
Nicolas | 19.6 | 87.75
Total | 148.2 | 262.35
Final Evaluation
Members | Estimated Hours | Worked hours
Nicolas | 26 | 83.8
Álefe | 4 | 108.25
Matheus | 4 | 38.31
Nathan | 4 | 30.47
Total | 38 | 260.83
Total
Members | Estimated Hours | Worked hours | Difference (%)
Nicolas | 151.77 | 293.4 | 93.3188
Matheus | 135.08 | 130.37 | -3.4868
Álefe | 133.08 | 273.5 | 105.5155
Nathan | 123.08 | 156.39 | 27.0637
Total | 543.01 | 853.66 | 57.2089