## Foreseen schedule 0 (hidden)
Subtitle | Status | Activity |  | Estimated Hours | Margin of error | Responsable | Team | Weeks
Planned Activity | [7 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total
Concluded Activity |  | Code | Description |  |  |  |  | 12 - 19/09 | 20 - 27/09 | 28/09 - 03/10 | 04 - 10/10 | 11 - 17/10 | 18 - 24/10 | 25 - 31/10 | 01 - 07/11 | 08 - 14/11 | 15 - 21/11 | 22 - 28/11 | 29/11 - 05/12 | 06 - 12/12
Late Activity | Planned Activity | M1 | Measure the hardware pieces | 0.041667 | 0.0125 | Enrico | Giuliana | [13 empty] | 0
in advance Activity | Planned Activity | M2 | Estimated space based on hardware's pieces sizes | 0.041667 | 0.0125 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | M3 | Think about hardware occupancy optimization | 0.083333 | 0.025 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | M4 | Develop Mechanical Design (Beautiful and Smart) | 0.125 | 0.0375 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | M5 | Engineering Research Mechanical & Gears | 0.125 | 0.0375 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | M6 | Search about spring or motor lock - decide which one to use | 0.083333 | 0.025 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | M7 | Modeling in Solidworks | 0.33333 | 0.1 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | H1 | IDE Arduino: Documentation reading and search tips | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H2 | IDE Arduino: Merge with GIT | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H3 | DC Motor: Search Specifications - datasheet, pinout, module need analysis, etc. | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H4 | DC Motor: DC Motor Power Tests | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H5 | DC Motor: DC Motor Power Consumption Test | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H6 | DC Motor: Lookup for existing codes and Software Response tests | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H7 | DC Motor: Software Modeling and Modularization | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H8 | DC Motor: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H9 | DC motor: Software module testing and adjusted for integration | 0.083333 | 0.025 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H10 | Voltage Regulator: Research and Analysis options | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H11 | Voltage Regulator: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H12 | Voltage Regulator: Autonomy Calculations | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H13 | Voltage Regulator: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H14 | Voltage Regulator: Autonomy Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H15 | Voltage Regulator: Power Consumption Test | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H16 | Gyroscope Module: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H17 | Gyroscope Module: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H18 | Gyroscope Module: Power Consumption Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H19 | Gyroscope Module: Code and Documentation Search | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H20 | Gyroscope Module: Software ResponseTest | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H21 | Gyroscope Module: Connection Test | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H22 | Gyroscope Module: Hardware Interruption Testing | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H23 | Bluetooth Module: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H24 | Bluetooth Module: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H25 | Bluetooth Module: Power Consumption Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H26 | Bluetooth Module: Code and Documentation Search | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H27 | Bluetooth Module: Software ResponseTest | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H28 | Bluetooth Module: SmartPhone Connection Test | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H29 | Bluetooth Module: Hardware Interruption Testing | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H30 | GSM/GPRS Module: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H31 | GSM/GPRS Module: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H32 | GSM/GPRS Module: Power Comsuption Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H33 | GSM/GPRS Module: Conde and documentation Search | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H34 | GSM/GPRS Module: Software Response Test | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H35 | GSM/GPRS Module: Smartphone Connection Test | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H36 | GSM/GPRS Module: Hardware Interruption Testing | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H37 | GPS Module: Search Specification - datasheet, pinout, etc. | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H38 | GPS Module: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H39 | GPS Module: Power Consumption Test | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H40 | GPS Module: Search for codes and documentation | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H41 | GPS Module: Software Response | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H42 | GPS Module: Smartphone and Internet connection test | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H43 | GPS Module: Hardware Interruption Tests | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H44 | Buzzer Module: Search specification - datasheet, pinout, power consumption, etc | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H45 | Buzzer Module: Power tests | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H46 | Buzzer Module: Power consumption tests | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H47 | Buzzer Module: Search codes and documentation | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H48 | Buzzer Module: Software response tests | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H49 | Power System: Search specification - datasheet, pinout, power consumption, etc | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H50 | Power System: Battery life analysis | 0.010417 | 0.003125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H51 | Power System: Battery life analysis | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H52 | Power System: Battery life test | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H53 | Power System: Power consumption | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H54 | Power System: Integration test with modules | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
Software | Planned Activity | H55 | Power System: Recharge test | 0.020833 | 0.00625 | Lucas | Marcelle | [13 empty] | 0
1899-12-31 11:06 | Planned Activity | S1 | Application business rules definition | 0.125 | 0.0375 | Giuliana | Marcelle | [13 empty] | 0
| Planned Activity | S2 | Plan and build use cases | 0.125 | 0.0375 | Giuliana | Marcelle | [13 empty] | 0
| Planned Activity | S3 | Create the mobile aplication mockups | 0.041667 | 0.0125 | Giuliana | Marcelle | [13 empty] | 0
| Planned Activity | S4 | Create the wireframes | 0.33333 | 0.1 | Giuliana | Marcelle | [13 empty] | 0
| Planned Activity | S5 | Flow chat with users access routine | 0.083333 | 0.025 | Giuliana | Marcelle | [13 empty] | 0
| Planned Activity | S6 | Storyboard - Marvel App | 0.083333 | 0.025 | Giuliana | Marcelle | [13 empty] | 0
| Planned Activity | S7 | Search about Flutter | 0.33333 | 0.1 | Giuliana | Marcelle | [13 empty] | 0
| Planned Activity | D1 | Structure the Final Report on Overleaf | 0.041667 | 0.0125 | Marcelle | Lucas | [13 empty] | 0
| Planned Activity | D2 | First checkpoint - Blog revision | 0.083333 | 0.025 | Marcelle | Lucas | [13 empty] | 0
|  |  |  | 1900-01-02 13:30 | 1899-12-31 01:39 |  |  | Weeks Week 1: 0; Weeks Week 2: 0
| Entrega | AV1 | Checkpoint 1 - 26/09
| Planned Activity | M8 | 3D Print - Parts | 0.20833 | 0.0625 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | M9 | Assemble parts | 0.20833 | 0.0625 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | I1 | Hardware and Mechanics: Lock test with DC motor | 0.125 | 0.0375 | Enrico e Lucas | [14 empty] | 0
| Planned Activity | M10 | Final adjusts - Mechanics | 0.20833 | 0.0625 | Enrico | Giuliana | [13 empty] | 0
| Planned Activity | H56 | Bluetooth Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H57 | Bluetooth Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H58 | Bluetooth Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H59 | GSM/GPRS Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H60 | GSM/GPRS Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H61 | GSM/GPRS Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H62 | GPS Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H63 | GPS Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H64 | GPS Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H65 | Buzzer Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H66 | Buzzer Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H67 | Buzzer Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H68 | (If necessary) Circuit Board layout | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H69 | Hardware Modules - Integration | 0.083333 | 0.025 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H70 | Hardware Modules Test | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | I2 | Hardware and Software: Specification of functions, inputs, outputs, etc. | 0.083333 | 0.025 | Lucas e Giuliana | [14 empty] | 0
| Planned Activity | I3 | Hardware and Mechanics: Integration Tests | 0.041667 | 0.0125 | Lucas e Enrico | [14 empty] | 0
| Planned Activity | D2 | Hardware Schematics | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | S8 | Backend: Search Backend details - Databases, API, Server, CloudServers, etc. | 0.041667 | 0.0125 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S9 | Backend: Tools Search - Choose API's | 0.020833 | 0.00625 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S10 | Backend: Tools Search - Define Database | 0.020833 | 0.00625 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S11 | Backend: Tools Search - Define Server | 0.020833 | 0.00625 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S12 | Backend: Tools Search - Define Storage app | 0.020833 | 0.00625 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S13 | Backend: Planning - Create model of Database - SQL or NoSQL | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S14 | Backend: Planning - Create diagrams with interaction between API's and other components | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S15 | Backend: Planning - Create diagrams with interaction between DB and Components Interactions | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S16 | Backend: Planning - Server and User usage flows. | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S17 | Backend: Planning - Defining diagrams and interaction flows | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S18 | Backend - Infra: Building Database Infrastructure | 0.041667 | 0.0125 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S19 | Backend - Infra: Configuring Database | 0.041667 | 0.0125 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S20 | Backend - Infra: Infrastructure - Servers | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S21 | Backend - Infra: Configuring Image Database - Storage | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S22 | Backend - Infra: Coding Image Database - Storage - Storage | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S23 | Backend - Infra: Server configuration - Webserver | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S24 | Backend - Infra: Server codification - Webserver | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S25 | Backend - Infra: Server configuration - Authentication | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S26 | Backend - Infra: Server codification - Authentication | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S27 | Backend - Infra: Server configuration - set DNS | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S28 | Backend - Infra: Server codification - set DNS | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S29 | Backend - Infra: Server configuration - Notifications | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S30 | Backend - Infra: Server codification - Notifications | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S31 | Align the information necessary to each page on Frontend, to link with the Backend. | 0.041667 | 0.0125 | Giuliana | Marcelle, Enrico, Lucas | [13 empty] | 0
SW - Front | Planned Activity | S32 | Frontend: develop map screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
0.975 | Planned Activity | S33 | Frontend: develop authentication screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S34 | Frontend: develop monetary transaction screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S35 | Frontend: develop tab to define the user | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S36 | Frontend: develop the locator options according with the tab | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S37 | Frontend: develop the tenant options according with the tab | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S38 | Frontend: develop the alarm screen and the pop-up | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S39 | Frontend: develop the Travel Screen - informing the price, the travel time and end button | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S40 | Frontend: Adjust screen navigation | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S41 | Backend: develop monetary transaction system - criptotransactions | 0.33333 | 0.1 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S42 | Backend: develop the map with the bike location | 0.33333 | 0.1 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S43 | Backend: develop the geofencing system | 0.33333 | 0.1 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S44 | Backend: develop authentication system | 0.33333 | 0.1 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S45 | Backend: develop camera system | 0.33333 | 0.1 | Enrico | Marcelle
| Planned Activity | S46 | Iniciate - Integrate Backend with Frontend | 0.083333 | 0.025 | Giuliana | Enrico, Lucas e Marcelle | [13 empty] | 0
| Planned Activity | D3 | Write the Introduction and resume | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | D4 | Write Project Functionalities Section | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | D5 | Write a Project Overview (Embeeded System, Base Station and Communication) | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | D6 | Final Report: Finalyze Development - Hardware Part | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | D7 | Final Report: Finalyze Development - Mechanics Part | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
|  |  |  | 1900-01-04 22:30 | 1900-01-02 13:03
| Entrega | AV2 | Checkpoint 2 - 17/10
| Planned Activity | S46 | Frontend: develop QRCode reader screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S47 | Frontend: develop travel history screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S48 | Frontend: develop Rating screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S49 | Frontend: develop Information Personal screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S50 | Finalyze - integrate Frontend and Backend | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | [13 empty] | 0
| Planned Activity | S51 | Backend: develop rating system | 0.20833 | 0.0625 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S52 | Backend: develop the available user or bikes according with user's rate | 0.20833 | 0.0625 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S53 | Backend: develop QRCode reader system | 0.20833 | 0.0625 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S54 | Backend: Develop the pictures system - to check the bike conditions | 0.20833 | 0.0625 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | S55 | Backend: implement the rent system - read QRCode and select the bike | 0.20833 | 0.0625 | Enrico | Marcelle | [13 empty] | 0
| Planned Activity | D8 | Final Report: Finalyze Development - Software Part | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | D9 | Final Report: Finalyze Development- integration Part | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | D10 | Final Report: Finalyze the Report - Final Considerations, Bibliograph | 0.20833 | 0.0625 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | I4 | Hardware and software: send GPS location to back-end | 0.20833 | 0.0625 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I5 | Hardware and software: send GPS location and test the Geofencing | 0.20833 | 0.0625 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I6 | Hardware and software: send info about the disable lock | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I7 | Hardware and software: send info about the enable lock | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I8 | Hardware and software: send Alarm notification to back-end | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I9 | Hardware and software: send ticket information to the server | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I10 | Lock system test | 0.16667 | 0.05 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I11 | Speed system test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I12 | Geofencing test | 0.083333 | 0.025 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I13 | Geolocation test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I14 | Alarm test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I15 | Payment system test | 0.083333 | 0.025 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I16 | Renting system test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I17 | User reports test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | D11 | Video: record the project working | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana
| Planned Activity | D12 | Video: edit and finish the video | 0.33333 | 0.1 | Marcelle | Enrico, Lucas e Giuliana
|  |  |  | 1900-01-02 19:00 | 1899-12-31 03:18
| Entrega | AV3 | Checkpoint 3 - 07/11
| Planned Activity | D1 | Iniciate - Correct and Review the Final Report | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
| Planned Activity | I18 | Final Hardware adjusts | 0.125 | 0.0375 | Lucas | Marcelle, Giuliana, Enrico | [13 empty] | 0
| Planned Activity | I19 | Final software adjusts | 0.083333 | 0.083333 | Giuliana | Marcelle, Lucas, Enrico | [13 empty] | 0
| Planned Activity | I20 | Final Integration adjusts | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I21 | Final tests | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
| Planned Activity | I22 | Final adjusts | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0
|  |  |  | 0.70833 | 0.27083
| Entrega | AVG | Avaliação Final - 28/11
| Planned Activity | D2 | Finalyze - Correct and Review the Final Report | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0
|  |  |  | 0.125 | 0.0375
| Entrega | RT | Final Report
0
0
0
Formulas:
Margin of error = ([Estimated Hours]/100)*30
Margin of error = SUM(H21:[Margin of error, row above])
Total = SUM([Weeks]:W5)
Subtitle = sum([Estimated Hours]:H73)
Subtitle = sum([Estimated Hours, row above]:H132)
Estimated Hours = SUM(G5:[Estimated Hours, row above])
Estimated Hours = SUM([Estimated Hours, row above])

## Foreseen schedule
Subtitle
Planned Activity
Concluded Activity | Status |  | Activity | Estimated Hours | Margin of error | Responsable | Team | Weeks
Late Activity | [7 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total
in advance Activity |  | Code | Description |  |  |  |  | 12 - 19/09 | 20 - 26/09 | 28/09 - 03/10 | 04 - 10/10 | 11 - 17/10 | 18 - 24/10 | 25 - 31/10 | 01 - 07/11 | 08 - 14/11 | 15 - 21/11 | 22 - 28/11 | 29/11 - 05/12 | 06 - 12/12
| Planned Activity | M1 | Measure the hardware pieces | 0.041667 | 0.0125 | Enrico | Giuliana | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | M2 | Estimated space based on hardware's pieces sizes | 0.041667 | 0.0125 | Enrico | Giuliana | Weeks Week 1: 0.020833; Weeks Week 2: 0.020833 | 0.041667
| Planned Activity | M3 | Think about hardware occupancy optimization | 0.083333 | 0.025 | Enrico | Giuliana | Weeks Week 1: 0.041667; Weeks Week 2: 0.041667 | 0.083333
| Planned Activity | M4 | Develop Mechanical Design (Beautiful and Smart) | 0.125 | 0.0375 | Enrico | Giuliana | Weeks Week 1: 0.0625; Weeks Week 2: 0.0625 | 0.125
| Planned Activity | M5 | Engineering Research Mechanical & Gears | 0.125 | 0.0375 | Enrico | Giuliana | Weeks Week 1: 0.0625; Weeks Week 2: 0.0625 | 0.125
| Planned Activity | M6 | Search about spring or motor lock - decide which one to use | 0.083333 | 0.025 | Enrico | Giuliana | Weeks Week 1: 0.041667; Weeks Week 2: 0.041667 | 0.083333
| Planned Activity | M7 | Modeling in Solidworks | 0.33333 | 0.1 | Enrico | Giuliana | Weeks Week 1: 0.16667; Weeks Week 2: 0.16667 | 0.33333
| Planned Activity | H1 | IDE Arduino: Documentation reading and search tips | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H2 | IDE Arduino: Merge with GIT | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H3 | DC Motor: Search Specifications - datasheet, pinout, module need analysis, etc. | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833
| Planned Activity | H4 | DC Motor: DC Motor Power Tests | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H5 | DC Motor: DC Motor Power Consumption Test | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833
| Planned Activity | H6 | DC Motor: Lookup for existing codes and Software Response tests | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H7 | DC Motor: Software Modeling and Modularization | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H8 | DC Motor: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | Weeks Week 1: 0.083333 | 0.083333
| Planned Activity | H9 | DC motor: Software module testing and adjusted for integration | 0.083333 | 0.025 | Lucas | Marcelle | Weeks Week 1: 0.083333 | 0.083333
| Planned Activity | H10 | Voltage Regulator: Research and Analysis options | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H11 | Voltage Regulator: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H12 | Voltage Regulator: Autonomy Calculations | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833
| Planned Activity | H13 | Voltage Regulator: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H14 | Voltage Regulator: Autonomy Test | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H15 | Voltage Regulator: Power Consumption Test | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833
| Planned Activity | H16 | Gyroscope Module: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H17 | Gyroscope Module: Power Test | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H18 | Gyroscope Module: Power Consumption Test | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H19 | Gyroscope Module: Code and Documentation Search | 0.020833 | 0.00625 | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833
| Planned Activity | H20 | Gyroscope Module: Software ResponseTest | 0.041667 | 0.0125 | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H21 | Gyroscope Module: Connection Test | 0.041667 | 0.0125 | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H22 | Gyroscope Module: Hardware Interruption Testing | 0.041667 | 0.0125 | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H23 | Bluetooth Module: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H24 | Bluetooth Module: Power Test | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H25 | Bluetooth Module: Power Consumption Test | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417
| Planned Activity | H26 | Bluetooth Module: Code and Documentation Search | 0.020833 | 0.00625 | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833
| Planned Activity | H27 | Bluetooth Module: Software ResponseTest | 0.041667 | 0.0125 | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H28 | Bluetooth Module: SmartPhone Connection Test | 0.041667 | 0.0125 | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H29 | Bluetooth Module: Hardware Interruption Testing | 0.041667 | 0.0125 | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | H30 | GSM/GPRS Module: Search Specifications - datasheet, pinout, etc | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H31 | GSM/GPRS Module: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H32 | GSM/GPRS Module: Power Comsuption Test | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H33 | GSM/GPRS Module: Conde and documentation Search | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 2: 0.020833 | 0.020833
| Planned Activity | H34 | GSM/GPRS Module: Software Response Test | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H35 | GSM/GPRS Module: Smartphone Connection Test | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H36 | GSM/GPRS Module: Hardware Interruption Testing | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H37 | GPS Module: Search Specification - datasheet, pinout, etc. | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H38 | GPS Module: Power Test | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H39 | GPS Module: Power Consumption Test | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H40 | GPS Module: Search for codes and documentation | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 2: 0.020833 | 0.020833
| Planned Activity | H41 | GPS Module: Software Response | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H42 | GPS Module: Smartphone and Internet connection test | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H43 | GPS Module: Hardware Interruption Tests | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H44 | Buzzer Module: Search specification - datasheet, pinout, power consumption, etc | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H45 | Buzzer Module: Power tests | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H46 | Buzzer Module: Power consumption tests | 0.010417 | 0.003125 | Marcelle | Lucas | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H47 | Buzzer Module: Search codes and documentation | 0.020833 | 0.00625 | Marcelle | Lucas | Weeks Week 2: 0.020833 | 0.020833
| Planned Activity | H48 | Buzzer Module: Software response tests | 0.020833 | 0.00625 | Marcelle | Lucas | Weeks Week 2: 0.020833 | 0.020833
| Planned Activity | H49 | Power System: Search specification - datasheet, pinout, power consumption, etc | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 2: 0.020833 | 0.020833
| Planned Activity | H50 | Power System: Battery life analysis | 0.010417 | 0.003125 | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417
| Planned Activity | H51 | Power System: Battery life analysis | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H52 | Power System: Battery life test | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H53 | Power System: Power consumption | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 2: 0.020833 | 0.020833
| Planned Activity | H54 | Power System: Integration test with modules | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667
| Planned Activity | H55 | Power System: Recharge test | 0.020833 | 0.00625 | Lucas | Marcelle | Weeks Week 2: 0.020833 | 0.020833
| Planned Activity | S1 | Application business rules definition | 0.125 | 0.0375 | Giuliana | Marcelle | Weeks Week 1: 0.125 | 0.125
| Planned Activity | S2 | Plan and build use cases | 0.125 | 0.0375 | Giuliana | Marcelle | Weeks Week 1: 0.125 | 0.125
| Planned Activity | S3 | Create the mobile aplication sketches | 0.041667 | 0.0125 | Giuliana | Marcelle | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | S4 | Create the wireframes | 0.33333 | 0.1 | Giuliana | Marcelle | Weeks Week 1: 0.33333 | 0.33333
| Planned Activity | S5 | Flow chat with users access routine | 0.083333 | 0.025 | Giuliana | Marcelle | Weeks Week 2: 0.083333 | 0.083333
| Planned Activity | S6 | Storyboard - Marvel App | 0.083333 | 0.025 | Giuliana | Marcelle | Weeks Week 2: 0.083333 | 0.083333
| Planned Activity | S7 | Search about Flutter | 0.33333 | 0.1 | Giuliana | Marcelle | Weeks Week 2: 0.33333 | 0.33333
| Planned Activity | D1 | Structure the Final Report on Overleaf | 0.041667 | 0.0125 | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667
| Planned Activity | D2 | First checkpoint - Blog revision | 0.083333 | 0.025 | Marcelle | Lucas | Weeks Week 2: 0.083333 | 0.083333
| Entrega | AV1 | Checkpoint 1 - 26/09
| Planned Activity | M8 | 3D Print - Parts | 0.20833 | 0.0625 | Enrico | Giuliana | Weeks Week 2: 0.069444; Weeks Week 3: 0.069444; Weeks Week 4: 0.069444 | 0.20833
| Planned Activity | M9 | Assemble parts | 0.20833 | 0.0625 | Enrico | Giuliana | Weeks Week 3: 0.10417; Weeks Week 4: 0.10417 | 0.20833
| Planned Activity | I1 | Hardware and Mechanics: Lock test with DC motor | 0.125 | 0.0375 | Enrico e Lucas |  | Weeks Week 3: 0.125 | 0.125
| Planned Activity | M10 | Final adjusts - Mechanics | 0.20833 | 0.0625 | Enrico | Giuliana | Weeks Week 4: 0.20833 | 0.20833
| Planned Activity | H56 | Bluetooth Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 3: 0.041667 | 0.041667
| Planned Activity | H57 | Bluetooth Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | Weeks Week 3: 0.083333 | 0.083333
| Planned Activity | H58 | Bluetooth Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | Weeks Week 3: 0.125 | 0.125
| Planned Activity | H59 | GSM/GPRS Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 3: 0.041667 | 0.041667
| Planned Activity | H60 | GSM/GPRS Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | Weeks Week 3: 0.083333 | 0.083333
| Planned Activity | H61 | GSM/GPRS Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | Weeks Week 3: 0.125 | 0.125
| Planned Activity | H62 | GPS Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 3: 0.041667 | 0.041667
| Planned Activity | H63 | GPS Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | Weeks Week 3: 0.083333 | 0.083333
| Planned Activity | H64 | GPS Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | Weeks Week 3: 0.125 | 0.125
| Planned Activity | H65 | Buzzer Module: Software Modules and Model | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 3: 0.041667 | 0.041667
| Planned Activity | H66 | Buzzer Module: Software Module Programming | 0.083333 | 0.025 | Lucas | Marcelle | Weeks Week 3: 0.083333 | 0.083333
| Planned Activity | H67 | Buzzer Module: Software Module Tests and adjusts for integration | 0.125 | 0.0375 | Lucas | Marcelle | Weeks Week 3: 0.125 | 0.125
| Planned Activity | H68 | (If necessary) Circuit Board layout | 0.041667 | 0.0125 | Lucas | Marcelle | [13 empty] | 0
| Planned Activity | H69 | Hardware Modules - Integration | 0.083333 | 0.025 | Lucas | Marcelle | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | H70 | Hardware Modules Test | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 4: 0.041667 | 0.041667
| Planned Activity | I2 | Hardware and Software: Specification of functions, inputs, outputs, etc. | 0.083333 | 0.025 | Lucas e Giuliana |  | Weeks Week 3: 0.083333 | 0.083333
| Planned Activity | I3 | Hardware and Mechanics: Integration Tests | 0.041667 | 0.0125 | Lucas e Enrico |  | Weeks Week 4: 0.041667 | 0.041667
| Planned Activity | D3 | Hardware Schematics | 0.041667 | 0.0125 | Lucas | Marcelle | Weeks Week 4: 0.041667 | 0.041667
| Planned Activity | S8 | Backend: Search Backend details - Databases, API, Server, CloudServers, etc. | 0.041667 | 0.0125 | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.041667 | 0.041667
| Planned Activity | S9 | Backend: Tools Search - Choose API's | 0.020833 | 0.00625 | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.020833 | 0.020833
| Planned Activity | S10 | Backend: Tools Search - Define Database | 0.020833 | 0.00625 | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.020833 | 0.020833
| Planned Activity | S11 | Backend: Tools Search - Define Server | 0.020833 | 0.00625 | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.020833 | 0.020833
| Planned Activity | S12 | Backend: Tools Search - Define Storage app | 0.020833 | 0.00625 | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.020833 | 0.020833
| Planned Activity | S13 | Backend: Planning - Create model of Database - SQL or NoSQL | 0.083333 | 0.025 | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S14 | Backend: Planning - Create diagrams with interaction between API's and other components | 0.083333 | 0.025 | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S15 | Backend: Planning - Create diagrams with interaction between DB and Components Interactions | 0.083333 | 0.025 | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S16 | Backend: Planning - Server and User usage flows. | 0.083333 | 0.025 | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S17 | Backend: Planning - Defining diagrams and interaction flows | 0.083333 | 0.025 | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S18 | Backend - Infra: Building Database Infrastructure | 0.041667 | 0.0125 | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.041667 | 0.041667
| Planned Activity | S19 | Backend - Infra: Configuring Database | 0.041667 | 0.0125 | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.041667 | 0.041667
| Planned Activity | S20 | Backend - Infra: Infrastructure - Servers | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833
| Planned Activity | S21 | Backend - Infra: Configuring Image Database - Storage | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833
| Planned Activity | S22 | Backend - Infra: Coding Image Database - Storage - Storage | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833
| Planned Activity | S23 | Backend - Infra: Server configuration - Webserver | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833
| Planned Activity | S24 | Backend - Infra: Server codification - Webserver | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833
| Planned Activity | S25 | Backend - Infra: Server configuration - Authentication | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 5: 0.020833 | 0.020833
| Planned Activity | S26 | Backend - Infra: Server codification - Authentication | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 5: 0.020833 | 0.020833
| Planned Activity | S27 | Backend - Infra: Server configuration - set DNS | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 5: 0.020833 | 0.020833
| Planned Activity | S28 | Backend - Infra: Server codification - set DNS | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 5: 0.020833 | 0.020833
| Planned Activity | S29 | Backend - Infra: Server configuration - Notifications | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 5: 0.020833 | 0.020833
| Planned Activity | S30 | Backend - Infra: Server codification - Notifications | 0.020833 | 0.00625 | Lucas | Marcelle, Enrico | Weeks Week 5: 0.020833 | 0.020833
| Planned Activity | S31 | Align the information necessary to each page on Frontend, to link with the Backend. | 0.041667 | 0.0125 | Giuliana | Marcelle, Enrico, Lucas | Weeks Week 3: 0.041667 | 0.041667
| Planned Activity | S32 | Frontend: develop map screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 3: 0.083333 | 0.083333
| Planned Activity | S33 | Frontend: develop authentication screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 3: 0.083333 | 0.083333
| Planned Activity | S34 | Frontend: develop monetary transaction screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S35 | Frontend: develop tab to define the user | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S36 | Frontend: develop the locator options according with the tab | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S37 | Frontend: develop the tenant options according with the tab | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.083333 | 0.083333
| Planned Activity | S38 | Frontend: develop the alarm screen and the pop-up | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 5: 0.083333 | 0.083333
| Planned Activity | S39 | Frontend: develop the Travel Screen - informing the price, the travel time and end button | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 5: 0.083333 | 0.083333
| Planned Activity | S40 | Frontend: Adjust screen navigation | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 5: 0.083333 | 0.083333
| Planned Activity | S41 | Backend: develop monetary transaction system - criptotransactions | 0.33333 | 0.1 | Enrico | Marcelle | Weeks Week 4: 0.16667; Weeks Week 5: 0.16667 | 0.33333
| Planned Activity | S42 | Backend: develop the map with the bike location | 0.33333 | 0.1 | Enrico | Marcelle | Weeks Week 4: 0.16667; Weeks Week 5: 0.16667 | 0.33333
| Planned Activity | S43 | Backend: develop the geofencing system | 0.33333 | 0.1 | Enrico | Marcelle | Weeks Week 4: 0.16667; Weeks Week 5: 0.16667 | 0.33333
| Planned Activity | S44 | Backend: develop authentication system | 0.33333 | 0.1 | Enrico | Marcelle | Weeks Week 4: 0.16667; Weeks Week 5: 0.16667 | 0.33333
| Planned Activity | S45 | Backend: develop camera system | 0.33333 | 0.1 | Enrico | Marcelle | Weeks Week 4: 0.16667; Weeks Week 5: 0.16667 | 0.33333
| Planned Activity | S46 | Iniciate - Integrate Backend with Frontend | 0.083333 | 0.025 | Giuliana | Enrico, Lucas e Marcelle | Weeks Week 5: 0.083333 | 0.083333
| Planned Activity | D4 | Write the Introduction and resume | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 3: 0.041667; Weeks Week 4: 0.041667 | 0.083333
| Planned Activity | D5 | Write Project Functionalities Section | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 3: 0.041667; Weeks Week 4: 0.041667 | 0.083333
| Planned Activity | D6 | Write a Project Overview (Embeeded System, Base Station and Communication) | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 4: 0.0625; Weeks Week 5: 0.0625 | 0.125
| Planned Activity | D7 | Final Report: Finalyze Development - Hardware Part | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 5: 0.083333 | 0.083333
| Planned Activity | D8 | Final Report: Finalyze Development - Mechanics Part | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 5: 0.083333 | 0.083333
| Planned Activity | D9 | Second checkpoint - Blog revision | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 5: 0.125 | 0.125
| Entrega | AV2 | Checkpoint 2 - 17/10
| Planned Activity | S47 | Frontend: develop QRCode reader screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 6: 0.083333 | 0.083333
| Planned Activity | S48 | Frontend: develop travel history screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 6: 0.083333 | 0.083333
| Planned Activity | S49 | Frontend: develop Rating screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 6: 0.083333 | 0.083333
| Planned Activity | S50 | Frontend: develop Information Personal screen | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 6: 0.083333 | 0.083333
| Planned Activity | S51 | Finalyze - integrate Frontend and Backend | 0.083333 | 0.025 | Giuliana | Marcelle, Enrico | Weeks Week 6: 0.083333 | 0.083333
| Planned Activity | S52 | Backend: develop rating system | 0.20833 | 0.0625 | Enrico | Marcelle | Weeks Week 7: 0.20833 | 0.20833
| Planned Activity | S53 | Backend: develop the available user or bikes according with user's rate | 0.20833 | 0.0625 | Enrico | Marcelle | Weeks Week 7: 0.20833 | 0.20833
| Planned Activity | S54 | Backend: develop QRCode reader system | 0.20833 | 0.0625 | Enrico | Marcelle | Weeks Week 7: 0.20833 | 0.20833
| Planned Activity | S55 | Backend: Develop the pictures system - to check the bike conditions | 0.20833 | 0.0625 | Enrico | Marcelle | Weeks Week 7: 0.20833 | 0.20833
| Planned Activity | S56 | Backend: implement the rent system - read QRCode and select the bike | 0.20833 | 0.0625 | Enrico | Marcelle | Weeks Week 7: 0.20833 | 0.20833
| Planned Activity | D10 | Final Report: Finalyze Development - Software Part | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 7: 0.0625; Weeks Week 8: 0.0625 | 0.125
| Planned Activity | D11 | Final Report: Finalyze Development- integration Part | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.125 | 0.125
| Planned Activity | D12 | Final Report: Finalyze the Report - Final Considerations, Bibliograph | 0.20833 | 0.0625 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 6: 0.20833 | 0.20833
| Planned Activity | I4 | Hardware and software: send GPS location to back-end | 0.20833 | 0.0625 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.20833 | 0.20833
| Planned Activity | I5 | Hardware and software: send GPS location and test the Geofencing | 0.20833 | 0.0625 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.20833 | 0.20833
| Planned Activity | I6 | Hardware and software: send info about the disable lock | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.125 | 0.125
| Planned Activity | I7 | Hardware and software: send info about the enable lock | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.125 | 0.125
| Planned Activity | I8 | Hardware and software: send Alarm notification to back-end | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.125 | 0.125
| Planned Activity | I9 | Hardware and software: send ticket information to the server | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.125 | 0.125
| Planned Activity | I10 | Lock system test | 0.16667 | 0.05 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.16667 | 0.16667
| Planned Activity | I11 | Speed system test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.125 | 0.125
| Planned Activity | I12 | Geofencing test | 0.083333 | 0.025 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.083333 | 0.083333
| Planned Activity | I13 | Geolocation test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.125 | 0.125
| Planned Activity | I14 | Alarm test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.125 | 0.125
| Planned Activity | I15 | Payment system test | 0.083333 | 0.025 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.083333 | 0.083333
| Planned Activity | I16 | Renting system test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.125 | 0.125
| Planned Activity | I17 | User reports test | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.125 | 0.125
| Planned Activity | D13 | Video: record the project working | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.125 | 0.125
| Planned Activity | D14 | Video: edit and finish the video | 0.33333 | 0.1 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.33333 | 0.33333
| Planned Activity | D15 | Third checkpoint - Blog revision | 0.083333 | 0.025 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.083333 | 0.083333
| Entrega | AV3 | Checkpoint 3 - 07/11
| Planned Activity | D16 | Iniciate - Correct and Review the Final Report | 0.20833 | 0.0625 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 9: 0.069444; Weeks Week 10: 0.069444; Weeks Week 11: 0.069444 | 0.20833
| Planned Activity | I18 | Final Hardware adjusts | 0.125 | 0.0375 | Lucas | Marcelle, Giuliana, Enrico | Weeks Week 9: 0.041667; Weeks Week 10: 0.041667; Weeks Week 11: 0.041667 | 0.125
| Planned Activity | I19 | Final software adjusts | 0.083333 | 0.083333 | Giuliana | Marcelle, Lucas, Enrico | Weeks Week 9: 0.027778; Weeks Week 10: 0.027778; Weeks Week 11: 0.027778 | 0.083333
| Planned Activity | I20 | Final Integration adjusts | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 9: 0.041667; Weeks Week 10: 0.041667; Weeks Week 11: 0.041667 | 0.125
| Planned Activity | I21 | Final tests | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 9: 0.041667; Weeks Week 10: 0.041667; Weeks Week 11: 0.041667 | 0.125
| Planned Activity | I22 | Final adjusts | 0.125 | 0.0375 | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 9: 0.041667; Weeks Week 10: 0.041667; Weeks Week 11: 0.041667 | 0.125
| Entrega | AVG | Avaliação Final - 28/11
| Planned Activity | D17 | Finalyze - Correct and Review the Final Report | 0.125 | 0.0375 | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 12: 0.0625; Weeks Week 13: 0.0625 | 0.125
| Entrega | RT | Final Report - 12/12
|  |  |  | 1900-01-13 21:00 | 1900-01-03 12:30 |  |  | 1899-12-31 23:00 | 1899-12-31 16:10 | 1899-12-31 19:10 | 1900-01-01 12:10 | 1899-12-31 15:30 | 0.625 | 1900-01-01 00:30 | 1899-12-31 16:30 | 0.26389 | 0.26389 | 0.26389 | 0.0625 | 0.0625 | 1900-01-13 20:00
Formulas:
Margin of error = ([Estimated Hours]/100)*30
Total = SUM([Weeks]:V6)

## Actual schedule
Status |  | Activity | Responsable | Team | Weeks
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Estimated hours | Estimated Difference
| Code | Description |  |  | 12 - 19/09 | 20 - 26/09 | 28/09 - 03/10 | 04 - 10/10 | 11 - 17/10 | 18 - 24/10 | 25 - 31/10 | 01 - 07/11 | 08 - 14/11 | 15 - 21/11 | 22 - 28/11 | 29/11 - 05/12 | 06 - 12/12
Concluded Activity | M1 | Measure the hardware pieces | Enrico | Giuliana | Weeks Week 1: 0.048611 | 0.048611 | 0.041667 | -0.0069444
Concluded Activity | M2 | Estimated space based on hardware's pieces sizes | Enrico | Giuliana | Weeks Week 1: 0.013889; Weeks Week 2: 0.083333 | 0.097222 | 0.041667 | -0.055556
Concluded Activity | M3 | Think about hardware occupancy optimization | Enrico | Giuliana | Weeks Week 1: 0.0625; Weeks Week 2: 0.125 | 0.1875 | 0.083333 | -0.10417
Concluded Activity | M4 | Develop Mechanical Design (Beautiful and Smart) | Enrico | Giuliana | Weeks Week 1: 0.14583; Weeks Week 2: 0.20833 | 0.35417 | 0.125 | -0.22917
Concluded Activity | M5 | Engineering Research Mechanical & Gears | Enrico | Giuliana | Weeks Week 1: 0.013889; Weeks Week 2: 0.16667 | 0.18056 | 0.125 | -0.055556
Concluded Activity | M6 | Search about spring or motor lock - decide which one to use | Enrico | Giuliana | Weeks Week 1: 0.020833; Weeks Week 2: 0.125 | 0.14583 | 0.083333 | -0.0625
Concluded Activity | M7 | Modeling in Solidworks | Enrico | Giuliana | Weeks Week 2: 0.41667 | 0.41667 | 0.33333 | -0.083333
Concluded Activity | H1 | IDE Arduino: Documentation reading and search tips | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H2 | IDE Arduino: Merge with GIT | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H3 | DC Motor: Search Specifications - datasheet, pinout, module need analysis, etc. | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H4 | DC Motor: DC Motor Power Tests | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H5 | DC Motor: DC Motor Power Consumption Test | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H6 | DC Motor: Lookup for existing codes and Software Response tests | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H7 | DC Motor: Software Modeling and Modularization | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H8 | DC Motor: Software Module Programming | Lucas | Marcelle | Weeks Week 1: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | H9 | DC motor: Software module testing and adjusted for integration | Lucas | Marcelle | Weeks Week 1: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | H10 | Voltage Regulator: Research and Analysis options | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H11 | Voltage Regulator: Search Specifications - datasheet, pinout, etc | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H12 | Voltage Regulator: Autonomy Calculations | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H13 | Voltage Regulator: Power Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H14 | Voltage Regulator: Autonomy Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H15 | Voltage Regulator: Power Consumption Test | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H16 | Gyroscope Module: Search Specifications - datasheet, pinout, etc | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H17 | Gyroscope Module: Power Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H18 | Gyroscope Module: Power Consumption Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H19 | Gyroscope Module: Code and Documentation Search | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667 | 0.020833 | -0.020833
Concluded Activity | H20 | Gyroscope Module: Software ResponseTest | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833 | 0.041667 | 0.020833
Concluded Activity | H21 | Gyroscope Module: Accurate and Connection Test | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833 | 0.041667 | 0.020833
Concluded Activity | H22 | Gyroscope Module: Hardware Interruption Testing | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833 | 0.041667 | 0.020833
Concluded Activity | H23 | Bluetooth Module: Search Specifications - datasheet, pinout, etc | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H24 | Bluetooth Module: Power Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H25 | Bluetooth Module: Power Consumption Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H26 | Bluetooth Module: Code and Documentation Search | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H27 | Bluetooth Module: Software ResponseTest | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H28 | Bluetooth Module: SmartPhone Connection Test | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833 | 0.041667 | 0.020833
Concluded Activity | H29 | Bluetooth Module: Hardware Interruption Testing | Marcelle | Lucas | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H30 | GSM/GPRS Module: Search Specifications - datasheet, pinout, etc | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H31 | GSM/GPRS Module: Power Test | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H32 | GSM/GPRS Module: Power Comsuption Test | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H33 | GSM/GPRS Module: Code and documentation Search | Lucas | Marcelle | Weeks Week 2: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H34 | GSM/GPRS Module: Software Response Test | Lucas | Marcelle | Weeks Week 2: 0.083333 | 0.083333 | 0.041667 | -0.041667
Concluded Activity | H35 | GSM/GPRS Module: Smartphone Connection Test | Lucas | Marcelle | Weeks Week 2: 0.083333 | 0.083333 | 0.041667 | -0.041667
Concluded Activity | H36 | GSM/GPRS Module: Hardware Interruption Testing | Lucas | Marcelle | Weeks Week 2: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H37 | GPS Module: Search Specification - datasheet, pinout, etc. | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H38 | GPS Module: Power Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H39 | GPS Module: Power Consumption Test | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H40 | GPS Module: Search for codes and documentation | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H41 | GPS Module: Software Response | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H42 | GPS Module: Smartphone and Internet connection test | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H43 | GPS Module: Hardware Interruption Tests | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.041667 | 0.03125
Concluded Activity | H44 | Buzzer Module: Search specification - datasheet, pinout, power consumption, etc | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H45 | Buzzer Module: Power tests | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H46 | Buzzer Module: Power consumption tests | Lucas | Marcelle | Weeks Week 2: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H47 | Buzzer Module: Search codes and documentation | Marcelle | Lucas | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H48 | Buzzer Module: Software response tests | Marcelle | Lucas | Weeks Week 1: 0.010417 | 0.010417 | 0.020833 | 0.010417
Concluded Activity | H49 | Power System: Search specification - datasheet, pinout, power consumption, etc | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H50 | Power System: Battery life analysis | Lucas | Marcelle | Weeks Week 1: 0.010417 | 0.010417 | 0.010417 | 0
Concluded Activity | H51 | Power System: Battery life analysis | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H52 | Power System: Battery life test | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H53 | Power System: Power consumption | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | H54 | Power System: Integration test with modules | Lucas | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | H55 | Power System: Recharge test | Lucas | Marcelle | Weeks Week 1: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | S1 | Application business rules definition | Giuliana | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.125 | 0.083333
Concluded Activity | S2 | Plan and build use cases | Giuliana | Marcelle | Weeks Week 1: 0.125 | 0.125 | 0.125 | 0
Concluded Activity | S3 | Create the mobile aplication sketches | Giuliana | Marcelle | Weeks Week 1: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | S4 | Create the wireframes | Giuliana | Marcelle | Weeks Week 1: 0.20833; Weeks Week 2: 0.33333 | 0.54167 | 0.33333 | -0.20833
Concluded Activity | S5 | Flowchart with users access routine | Giuliana | Marcelle | Weeks Week 1: 0.125; Weeks Week 2: 0.125 | 0.25 | 0.083333 | -0.16667
Concluded Activity | S6 | Storyboard - Marvel App | Giuliana | Marcelle | Weeks Week 2: 0 | 0 | 0.083333 | 0.083333
Concluded Activity | S7 | Search about Flutter and install aplications needed | Giuliana | Marcelle | Weeks Week 2: 0.125 | 0.125 | 0.33333 | 0.20833
Concluded Activity | D1 | Structure the Final Report on Overleaf | Marcelle | Lucas | Weeks Week 1: 0.10417; Weeks Week 2: 0.083333 | 0.1875 | 0.041667 | -0.14583
Concluded Activity | D2 | First checkpoint - Blog revision | Marcelle | Lucas | Weeks Week 2: 0.16667 | 0.16667 | 0.083333 | -0.083333
Entrega | AV1 | Checkpoint 1 - 26/09
Concluded Activity | M8 | 3D Print - Parts | Enrico | Giuliana | Weeks Week 2: 0.020833; Weeks Week 3: 0.020833; Weeks Week 4: 1899-12-31 04:00; Weeks Week 5: 0.375 | 1899-12-31 14:00 | 0.20833 | -1.375
Concluded Activity | H56 | Bluetooth Module: Software Modules and Model | Lucas | Marcelle | Weeks Week 3: 0.036806 | 0.036806 | 0.041667 | 0.0048611
Concluded Activity | H57 | Bluetooth Module: Software Module Programming | Lucas | Marcelle | Weeks Week 4: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | H58 | Bluetooth Module: Software Module Tests and adjusts for integration | Lucas | Marcelle | Weeks Week 4: 0.125 | 0.125 | 0.125 | 0
Concluded Activity | H59 | GSM/GPRS Module: Software Modules and Model | Lucas | Marcelle | Weeks Week 3: 0.036806 | 0.036806 | 0.041667 | 0.0048611
Concluded Activity | H60 | GSM/GPRS Module: Software Module Programming | Lucas | Marcelle | Weeks Week 4: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | H61 | GSM/GPRS Module: Software Module Tests and adjusts for integration | Lucas | Marcelle | Weeks Week 4: 0.125 | 0.125 | 0.125 | 0
Concluded Activity | H62 | GPS Module: Software Modules and Model | Lucas | Marcelle | Weeks Week 3: 0.036806 | 0.036806 | 0.041667 | 0.0048611
Concluded Activity | H63 | GPS Module: Software Module Programming | Lucas | Marcelle | Weeks Week 4: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | H64 | GPS Module: Software Module Tests and adjusts for integration | Lucas | Marcelle | Weeks Week 4: 0.125 | 0.125 | 0.125 | 0
Concluded Activity | H65 | Buzzer Module: Software Modules and Model | Lucas | Marcelle | Weeks Week 3: 0.036806 | 0.036806 | 0.041667 | 0.0048611
Concluded Activity | H66 | Buzzer Module: Software Module Programming | Lucas | Marcelle | Weeks Week 4: 0.041667 | 0.041667 | 0.083333 | 0.041667
Concluded Activity | H67 | Buzzer Module: Software Module Tests and adjusts for integration | Lucas | Marcelle | Weeks Week 4: 0.041667 | 0.041667 | 0.125 | 0.083333
Concluded Activity | H68 | Circuit Board layout + Soldering Componens | Lucas | Marcelle | Weeks Week 3: 0.083333; Weeks Week 4: 0.125; Weeks Week 5: 0.041667 | 0.25 | 0.041667 | -0.25
Concluded Activity | H69 | Hardware Modules - Integration | Lucas | Marcelle | Weeks Week 4: 0.375; Weeks Week 5: 0.083333 | 0.45833 | 0.083333 | -0.375
Concluded Activity | I2 | Hardware and Software: Specification of functions, inputs, outputs, etc. | Lucas e Giuliana |  | Weeks Week 3: 0.16667 | 0.16667 | 0.083333 | -0.083333
Concluded Activity | D3 | Hardware Schematics | Lucas | Marcelle | Weeks Week 4: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | S8 | Backend: Search Backend details - Databases, API, Server, CloudServers, etc. | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.125 | 0.125 | 0.041667 | -0.083333
Concluded Activity | S9 | Backend: Tools Search - Choose API's | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.010417 | 0.010417 | 0.020833 | 0.010417
Concluded Activity | S10 | Backend: Tools Search - Define Database | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | S11 | Backend: Tools Search - Define Server | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | S12 | Backend: Tools Search - Define Storage app | Marcelle, Enrico, Lucas | Giuliana | Weeks Week 3: 0.020833 | 0.020833 | 0.020833 | 0
Revoked activity | S14 | Backend: Planning - Create diagrams with interaction between API's and other components | Marcelle, Enrico | Giuliana | [13 empty] | 0 | 0.083333 | 0.083333
Revoked activity | S15 | Backend: Planning - Create diagrams with interaction between DB and Components Interactions | Marcelle, Enrico | Giuliana | [13 empty] | 0 | 0.083333 | 0.083333
Concluded Activity | S16 | Backend: Planning - Server and User usage flows. | Marcelle, Enrico | Giuliana | Weeks Week 3: 0.16667 | 0.16667 | 0.083333 | -0.083333
Concluded Activity | S17 | Backend: Planning - Defining diagrams and interaction flows | Marcelle, Enrico | Giuliana | Weeks Week 4: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | S18 | Backend - Infra: Building Database Infrastructure | Lucas | Giuliana | Weeks Week 4: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | S19 | Backend - Infra: Configuring Database | Lucas | Giuliana | Weeks Week 4: 0.041667 | 0.041667 | 0.041667 | 0
Concluded Activity | S20 | Backend - Infra: Infrastructure - Servers | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | S21 | Backend - Infra: Configuring Image Database - Storage | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833 | 0.020833 | 0
Revoked activity | S23 | Backend - Infra: Server configuration - Webserver | Lucas | Marcelle, Enrico | [13 empty] | 0 | 0.020833 | 0.020833
Revoked activity | S24 | Backend - Infra: Server codification - Webserver | Lucas | Marcelle, Enrico | [13 empty] | 0 | 0.020833 | 0.020833
Concluded Activity | S25 | Backend - Infra: Server configuration - Authentication | Lucas | Marcelle, Enrico | Weeks Week 4: 0.020833 | 0.020833 | 0.020833 | 0
Revoked activity | S27 | Backend - Infra: Server configuration - set DNS | Lucas | Marcelle, Enrico | [13 empty] | 0 | 0.020833 | 0.020833
Revoked activity | S28 | Backend - Infra: Server codification - set DNS | Lucas | Marcelle, Enrico | [13 empty] | 0 | 0.020833 | 0.020833
Concluded Activity | S31 | Align the information necessary to each page on Frontend, to link with the Backend. | Giuliana | Marcelle, Enrico, Lucas | Weeks Week 3: 0.16667 | 0.16667 | 0.041667 | -0.125
Concluded Activity | S32 | Frontend: develop map screen | Giuliana | Marcelle, Enrico | Weeks Week 3: 0.41667; Weeks Week 4: 0.09375 | 0.51042 | 0.083333 | -0.42708
Concluded Activity | S35 | Frontend: develop tab to define the user | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | S37 | Frontend: develop the tenant options according with the tab | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.16667 | 0.16667 | 0.083333 | -0.083333
Concluded Activity | S39 | Frontend: develop the Travel Screen - informing the price, the travel time and end button | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.16667 | 0.16667 | 0.083333 | -0.083333
Concluded Activity | S57 | Backend: develop QR Code System |  |  | Weeks Week 4: 0.125 | 0.125 | 0:00 | -0.041667
Concluded Activity | S46 | Initiate - Integrate Backend with Frontend | Giuliana | Enrico, Lucas e Marcelle | Weeks Week 4: 0.083333; Weeks Week 5: 0.083333 | 0.16667 | 0.083333 | -0.083333
Concluded Activity | D4 | Write the Introduction and Requirements | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 2: 0.0625 | 0.0625 | 0.083333 | 0.020833
Concluded Activity | D5 | Write Project Functionalities Section | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 2: 0.041667 | 0.041667 | 0.083333 | 0.041667
Concluded Activity | D6 | Write a Project Overview (Embeeded System, Base Station and Communication) | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 2: 0.041667 | 0.041667 | 0.125 | 0.083333
Concluded Activity | D9 | Second checkpoint - Blog revision | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 5: 0.125 | 0.125 | 0.125 | 0
Entrega | AV2 | Checkpoint 2 - 17/10
Concluded Activity | M9 | Assemble parts | Enrico | Giuliana | Weeks Week 3: 0.020833; Weeks Week 4: 0.083333; Weeks Week 5: 0.20833; Weeks Week 6: 0.083333; Weeks Week 8: 0.125 | 0.52083 | 0.20833 | -0.3125
Concluded Activity | I1 | Hardware and Mechanics: Lock test with DC motor | Enrico e Lucas |  | Weeks Week 6: 0.010417 | 0.010417 | 0.125 | 0.11458
Concluded Activity | M10 | Final adjusts - Mechanics | Enrico | Giuliana | Weeks Week 5: 0.083333; Weeks Week 6: 0.20833 | 0.29167 | 0.20833 | -0.083333
Concluded Activity | H70 | Hardware Modules Test | Lucas | Marcelle | Weeks Week 6: 0.375; Weeks Week 7: 0.83333 | 1899-12-31 05:00 | 0.041667 | -1.1667
Concluded Activity | I3 | Hardware and Mechanics: Integration Tests | Lucas e Enrico |  | Weeks Week 6: 0.041667; Weeks Week 7: 0.25 | 0.29167 | 0.041667 | -0.25
Concluded Activity | S13 | Backend: Planning - Create model of Database - NoSQL | Marcelle, Enrico | Giuliana | Weeks Week 6: 0.125 | 0.125 | 0.083333 | -0.041667
Concluded Activity | S22 | Backend - Infra: Coding Image Database - Storage - Storage | Lucas | Marcelle, Enrico | Weeks Week 6: 0.041667 | 0.041667 | 0.020833 | -0.020833
Concluded Activity | S26 | Backend - Infra: Server codification - Authentication | Lucas | Marcelle, Enrico | Weeks Week 6: 0.020833 | 0.020833 | 0.020833 | 0
Concluded Activity | S29 | Backend - Infra: Server configuration - Notifications | Lucas | Marcelle, Enrico | Weeks Week 7: 0.041667 | 0.041667 | 0.020833 | -0.020833
Concluded Activity | S30 | Backend - Infra: Server codification - Notifications | Lucas | Marcelle, Enrico | Weeks Week 7: 0.055556 | 0.055556 | 0.020833 | -0.034722
Concluded Activity | S33 | Frontend: develop authentication screen | Giuliana | Marcelle, Enrico | Weeks Week 6: 0.083333 | 0.083333 | 0.083333 | 0
Concluded Activity | S34 | Frontend: develop monetary transaction screen | Giuliana | Marcelle, Enrico | Weeks Week 5: 0.041667; Weeks Week 6: 0.14583 | 0.1875 | 0.083333 | -0.10417
Revoked activity | S36 | Frontend: develop the locator options according with the tab | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.16667; Weeks Week 5: 0.083333 | 0.25 | 0.083333 | -0.16667
Concluded Activity | S38 | Frontend: develop the alarm screen and the pop-up | Giuliana | Marcelle, Enrico | Weeks Week 7: 0.027778 | 0.027778 | 0.083333 | 0.055556
Concluded Activity | S40 | Frontend: Adjust screen navigation | Enrico | Marcelle, Enrico | Weeks Week 4: 0.083333; Weeks Week 5: 0.041667; Weeks Week 6: 0.16667; Weeks Week 7: 0.33333 | 0.625 | 0.083333 | -0.54167
Concluded Activity | S61 | Backend: develop monetary transaction system - blubler credits |  |  | Weeks Week 7: 0.41667 | 0.41667
Concluded Activity | S41 | Backend: develop monetary transaction system - criptotransactions | Enrico | Marcelle | Weeks Week 7: 0.375 | 0.375 | 0.33333 | -0.041667
Concluded Activity | S42 | Backend: develop the map with the bike location |  | Marcelle | Weeks Week 4: 0.09375; Weeks Week 5: 0.125; Weeks Week 8: 0.22917 | 0.44792 | 0.33333 | -0.11458
Revoked activity | S43 | Backend: develop the geofencing system | Enrico | Marcelle | [13 empty] | 0 | 0.33333 | 0.33333
Concluded Activity | S44 | Backend: develop authentication system | Enrico | Marcelle | Weeks Week 6: 0.10417 | 0.10417 | 0.33333 | 0.22917
Concluded Activity | S45 | Backend: develop camera system | Enrico | Marcelle | Weeks Week 4: 0.083333; Weeks Week 5: 0; Weeks Week 6: 0.125; Weeks Week 7: 0.083333 | 0.29167 | 0.33333 | 0.041667
Concluded Activity | S58 | Backend: develop bluetooth communication |  |  | Weeks Week 6: 0.29167; Weeks Week 7: 0.45833; Weeks Week 8: 0.125 | 0.875 | 0 | -0.79167
Concluded Activity | D7 | Final Report: Finalyze Development - Hardware Part | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.22917 | 0.22917 | 0.083333 | -0.14583
Concluded Activity | D8 | Final Report: Finalyze Development - Mechanics Part | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.10417 | 0.10417 | 0.083333 | -0.020833
Concluded Activity | S47 | Frontend: develop QRCode reader screen | Giuliana | Marcelle, Enrico | Weeks Week 4: 0.1875 | 0.1875 | 0.083333 | -0.10417
Concluded Activity | S48 | Frontend: develop travel history screen | Giuliana | Marcelle, Enrico | Weeks Week 6: 0.083333; Weeks Week 7: 0.041667 | 0.125 | 0.083333 | -0.041667
Concluded Activity | S49 | Frontend: develop Rating screen | Giuliana | Marcelle, Enrico | [13 empty] | 0 | 0.083333 | 0.083333
Concluded Activity | S50 | Frontend: develop Information Personal screen | Giuliana | Marcelle, Enrico | [13 empty] | 0 | 0.083333 | 0.083333
Concluded Activity | S51 | Finalyze - integrate Frontend and Backend | Giuliana | Marcelle, Enrico | Weeks Week 7: 0.625 | 0.625 | 0.083333 | -0.54167
Concluded Activity | S52 | Backend: develop rating system | Enrico | Marcelle | Weeks Week 7: 0.125 | 0.125 | 0.20833 | 0.083333
Revoked activity | S53 | Backend: develop the available user or bikes according with user's rate | Enrico | Marcelle | [13 empty] | 0 | 0.20833 | 0.20833
Concluded Activity | S54 | Backend: develop QRCode reader system | Enrico | Marcelle | [13 empty] | 0 | 0.20833 | 0.20833
Concluded Activity | S55 | Backend: Develop the pictures system - to check the bike conditions | Enrico | Marcelle | Weeks Week 6: 0.125; Weeks Week 7: 0.0625 | 0.1875 | 0.20833 | 0.020833
Concluded Activity | S56 | Backend: implement the rent system - read QRCode and select the bike | Enrico | Marcelle | Weeks Week 6: 0.25; Weeks Week 7: 0.5 | 0.75 | 0.20833 | -0.54167
Concluded Activity | D10 | Final Report: Finalyze Development - Software Part | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 7: 0.083333; Weeks Week 8: 0.052083 | 0.13542 | 0.125 | -0.010417
Concluded Activity | D11 | Final Report: Finalyze Development- integration Part | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.09375 | 0.09375 | 0.125 | 0.03125
Concluded Activity | D12 | Final Report: Finalyze the Report - Final Considerations, Bibliograph | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.22917 | 0.22917 | 0.20833 | -0.020833
Concluded Activity | I4 | Hardware and software: send GPS location to back-end | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.25 | 0.25 | 0.20833 | -0.041667
Revoked activity | I5 | Hardware and software: send GPS location and test the Geofencing | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 | 0.20833 | 0.20833
Revoked activity | S57 | Frontend: send info about the disable lock | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 |  | 0.125
Revoked activity | S58 | Frontend: send info about the enable lock | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 |  | 0.125
Concluded Activity | S59 | Frontend: sign in a new bike |  |  | Weeks Week 7: 0.083333 | 0.083333 |  | 0.041667
Concluded Activity | S60 | Frontend: screen with informations about bike's user |  |  | Weeks Week 7: 0.041667 | 0.041667 |  | 0.083333
Concluded Activity | S62 | Frontend: User data class |  |  | Weeks Week 7: 0.083333 | 0.083333 |  | 0.083333
Concluded Activity | S63 | Frontend: set timer |  |  | Weeks Week 7: 0.125 | 0.125 |  | 0
Concluded Activity | S64 | Frontend: screen to sign in wallet |  |  | Weeks Week 7: 0.041667 | 0.041667 |  | 0.041667
Concluded Activity | S65 | Backend: Google functions |  |  | Weeks Week 7: 1899-12-31 14:00; Weeks Week 8: 0.25 | 1899-12-31 20:00 |  | -1.7083
Concluded Activity | I8 | Hardware and software: send Alarm notification to back-end | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 7: 0.125 | 0.125 | 0.125 | 0
Revoked activity | I9 | Hardware and software: send ticket information to the server | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 | 0.125 | 0.125
Concluded Activity | I10 | Lock system test | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.083333 | 0.083333 | 0.16667 | 0.083333
Revoked activity | I11 | Speed system test | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 | 0.125 | 0.125
Revoked activity | I12 | Geofencing test | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 | 0.083333 | 0.083333
Concluded Activity | I13 | Geolocation test | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.020833 | 0.020833 | 0.125 | 0.10417
Concluded Activity | I14 | Alarm test | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.020833 | 0.020833 | 0.125 | 0.10417
Concluded Activity | I15 | Payment system test | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.020833 | 0.020833 | 0.083333 | 0.0625
Concluded Activity | I16 | Renting system test | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.083333 | 0.083333 | 0.125 | 0.041667
Concluded Activity | I17 | User reports test | Enrico, Giuliana, Lucas e Marcelle |  | Weeks Week 8: 0.25 | 0.25 | 0.125 | -0.125
Planned Activity | D13 | Video: record the project working | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0 | 0.125 | 0.125 | bar: Weeks Week 9
Planned Activity | D14 | Video: edit and finish the video | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.47222 | 0.47222 | 0.33333 | -0.13889
Concluded Activity | D15 | Third checkpoint - Blog revision | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.041667 | 0.041667 | 0.083333 | 0.041667
Concluded Activity | D18 | Write the Resume | Marcelle | Enrico, Lucas e Giuliana | Weeks Week 8: 0.041667 | 0.041667
Entrega | AV3 | Checkpoint 3 - 07/11
Planned Activity | D16 | Iniciate - Correct and Review the Final Report | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0 | 0.20833 | 0.20833 | bar: Weeks Week 9 to Weeks Week 11
Planned Activity | D17 | Organize Final Presentation | bar: Weeks Week 9
Planned Activity | I18 | Final Hardware adjusts | Lucas | Marcelle, Giuliana, Enrico | [13 empty] | 0 | 0.125 | 0.125 | bar: Weeks Week 9 to Weeks Week 11
Planned Activity | I19 | Final software adjusts | Giuliana | Marcelle, Lucas, Enrico | Weeks Week 8: 0.125 | 0.125 | 0.083333 | -0.041667
Planned Activity | I20 | Final Integration adjusts | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 | 0.125 | 0.125 | bar: Weeks Week 9 to Weeks Week 11
Planned Activity | I21 | Final tests | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 | 0.125 | 0.125 | bar: Weeks Week 9 to Weeks Week 11
Planned Activity | I22 | Final adjusts | Enrico, Giuliana, Lucas e Marcelle | [14 empty] | 0 | 0.125 | 0.125 | bar: Weeks Week 9 to Weeks Week 11
Entrega | AVG | Avaliação Final - 28/11
Planned Activity | D17 | Finalyze - Correct and Review the Final Report | Marcelle | Enrico, Lucas e Giuliana | [13 empty] | 0 | 0.125 | 0.125 | bar: Weeks Week 12 to Weeks Week 13
Entrega | RT | Final Report - 12/12
Total |  |  |  |  | 1900-01-01 03:05 | 1900-01-01 09:45 | 1899-12-31 09:17 | 1900-01-03 01:30 | 1899-12-31 07:00 | 1900-01-01 06:45 | 1900-01-05 15:30 | 1900-01-01 14:20 | 0 | 0 | 0 | 0 | 0 | 1900-01-21 19:12 | 1900-01-13 15:00 | -6.5917
Formulas:
Total = SUM([Weeks]:T4)
Estimated hours = VLOOKUP([AV1],'Foreseen schedule'!D6:F186,3,FALSE)
Estimated Difference = 'Foreseen schedule'!W6-[Total]

## Team - Clock in
Team Member | Worked Hours | [64 empty] | Total | Clock-in
| Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 | [5 empty] | Mechanical | 1900-01-03 08:20
| 12 - 19/09 |  |  |  |  | 20 - 26/09 |  |  |  |  | 28/09 - 03/10 |  |  |  |  | 04 - 10/10 |  |  |  |  | 11 - 17/10 |  |  |  |  | 18 - 24/10 |  |  |  |  | 25 - 31/10 |  |  |  |  | 01 - 07/11 |  |  |  |  | 08 - 14/11 |  |  |  |  | 15 - 21/11 |  |  |  |  | 22 - 28/11 |  |  |  |  | 29/11 - 05/12 |  |  |  |  | 06 - 12/12 | [5 empty] | Hardware | 1900-01-03 17:32
| M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I | M | H | S | D | I |  | Software | 1900-01-10 00:25
Enrico Manfron | 12 - 19/09 M: 0.30556; 20 - 26/09 M: 1899-12-31 03:00; 28/09 - 03/10 S: 0.083333; 28/09 - 03/10 I: 0.16667; 04 - 10/10 M: 1899-12-31 06:00; 04 - 10/10 S: 0.20833; 11 - 17/10 M: 0.66667; 18 - 24/10 M: 0.29167; 18 - 24/10 S: 0.083333; 18 - 24/10 I: 0.052083; 25 - 31/10 S: 1899-12-31 23:00; 25 - 31/10 I: 0.041667; 01 - 07/11 M: 0.45833; 01 - 07/11 S: 0.16667; 01 - 07/11 D: 0.25; 01 - 07/11 I: 0.083333 | 1900-01-06 04:35 | Documentation | 1899-12-31 23:50
Giuliana Martins | 12 - 19/09 S: 1899-12-31 04:00; 20 - 26/09 M: 0.083333; 28/09 - 03/10 S: 0.41667; 28/09 - 03/10 I: 0.16667; 04 - 10/10 M: 0.083333; 04 - 10/10 S: 0.85417; 18 - 24/10 S: 0.3125; 25 - 31/10 S: 1899-12-31 05:30; 01 - 07/11 S: 0.5625; 01 - 07/11 D: 0.125; 01 - 07/11 I: 0.083333 | 1900-01-04 02:00 | Integration | 1899-12-31 06:30
Lucas Ricardo | 12 - 19/09 H: 1899-12-31 04:00; 28/09 - 03/10 H: 0.22917; 28/09 - 03/10 S: 0.16667; 28/09 - 03/10 I: 0.16667; 04 - 10/10 H: 1899-12-31 12:32; 04 - 10/10 S: 0.16667; 18 - 24/10 H: 0.375; 18 - 24/10 S: 0.0625; 18 - 24/10 I: 0.010417; 25 - 31/10 H: 0.83333; 25 - 31/10 S: 0.125; 25 - 31/10 I: 0.29167; 01 - 07/11 M: 0.083333; 01 - 07/11 H: 0.041667; 01 - 07/11 S: 0.041667; 01 - 07/11 D: 0.53472; 01 - 07/11 I: 0.041667 | 1900-01-04 20:37 | Total | 1900-01-22 08:37
Marcelle Pires | 12 - 19/09 H: 0.29167; 12 - 19/09 D: 0.10417; 20 - 26/09 D: 0.39583; 28/09 - 03/10 H: 0.27083; 28/09 - 03/10 S: 0.13542; 28/09 - 03/10 I: 0.16667; 04 - 10/10 S: 0.54167; 04 - 10/10 D: 0.125; 11 - 17/10 D: 0.125; 18 - 24/10 S: 0.29167; 18 - 24/10 D: 0.041667; 25 - 31/10 S: 1899-12-31 19:00; 01 - 07/11 S: 0.65278; 01 - 07/11 D: 0.20833; 08 - 14/11 D: 0.083333 | 1900-01-04 05:25
Total | 0.30556 | 1899-12-31 11:00 | 1899-12-31 04:00 | 0.10417 | 0 | 1899-12-31 05:00 | 0 | 0 | 0.39583 | 0 | 0 | 0.5 | 0.80208 | 0 | 0.66667 | 1899-12-31 08:00 | 1899-12-31 12:32 | 1899-12-31 18:30 | 0.125 | 0 | 0.66667 | 0 | 0 | 0.125 | 0 | 0.29167 | 0.375 | 0.75 | 0.041667 | 0.0625 | 0 | 0.83333 | 1900-01-04 02:30 | 0 | 0.33333 | 0.54167 | 0.041667 | 1899-12-31 10:10 | 1899-12-31 02:50 | 0.20833 | 0 | 0 | 0 | 0.083333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900-01-22 08:37
Formulas:
Total = SUM([Worked Hours]:BO6)

## Team Reports
AV1 |  | AV2 |  | AV3 |  | Final Report
Planned Hours | 1900-01-02 13:30 | Planned Hours | 1900-01-05 01:30 | Planned Hours | 1900-01-03 08:00 | Planned Hours | 1900-01-12 23:00
Extra Planned H. | 1899-12-31 01:21 | Extra Planned H. | 1899-12-31 18:09 | Extra Planned H. | 1899-12-31 07:12 | Extra Planned H. | 1900-01-03 02:42
Worked Hours | 1900-01-03 12:50 | Worked Hours | 1900-01-05 17:47 | Worked Hours | 1900-01-10 12:35 | Worked Hours | 1900-01-21 19:12
Hours/member | 0.56684 | Hours/member | 1899-12-31 16:27 | Hours/member | 1900-01-01 21:09 | Hours/member | 1900-01-04 16:48
[6 empty] | Hours/week | 0.7125
|  | Late hours | 0
|  | Late act worked | 0
|  | Late | 0

## Mesures
| Worked | Planned | Extra | Total planned
Mechanical | 1900-01-02 19:50 | 1899-12-31 11:00 | 0.4375 | 1899-12-31 21:30 | Tasks Planned | Tasks worked | Revolked
Hardware | 1900-01-03 05:32 | 1900-01-01 15:30 | 0.79375 | 1900-01-02 10:33 | 175 | 170 | 15
Software | 1900-01-10 06:45 | 1900-01-04 23:30 | 1899-12-31 19:03 | 1900-01-06 18:33
Documentation | 1900-01-01 00:20 | 1900-01-01 02:00 | 0.625 | 1900-01-01 17:00
Integration | 1899-12-31 10:45 | 1900-01-01 11:00 | 0.87083 | 1900-01-02 07:54
Total | 1900-01-21 19:12 | 1900-01-13 15:00 | 1900-01-03 12:30 | 1900-01-18 03:30
Total/Member | 1900-01-04 16:48 | 1900-01-02 15:45 | 1899-12-31 03:07 | 1900-01-03 18:52
0.19086
Formulas:
Worked = SUM(C3:[Worked, row above])
Worked = [Worked, row above]/4
Total planned = [Extra]+[Planned]